## Indicative PPMP (2)
Republic of the Philippines Department of Education Cordillera Administrative Region SCHOOLS DIVISION OF BAGUIO CITY
PROJECT PROCUREMENT MANAGEMENT PLAN (PPMP) NO. ___
[5 empty] | INDICATIVE |  | FINAL
Fiscal Year :
End-User or Implementing Unit:
PROCUREMENT PROJECT DETAILS |  |  |  |  | PROJECTED TIMELINE (MM/YYYY) |  |  | FUNDING DETAILS |  | ATTACHED SUPPORTING DOCUMENTS | REMARKS
General Description and Objective of the Project to be Procured | Type of the Project to be Procured (whether Goods, Infrastructure and Consulting Services) | Quantity and Size of the Project to be Procured | Recommended Mode of Procurement | Pre-Procurement Conference, if applicable (Yes/No) | Start of Procurement Activity | End of Procurement Activity | Expected Delivery/ Implementation Period | Source of Funds | Estimated Budget / Authorized Budgetary Allocation (PhP)
Column 1 | Column 2 | Column 3 | Column 4 | Column 5 | Column 6 | Column 7 | Column 8 | Column 9 | Column 10 | Column 11 | Column 12
Refers to the type of procurement—whether for Goods (e.g., supplies, materials, ICT equipment, medicines); Infrastructure Projects (e.g., roads, buildings, site development or land improvement, public utilities such as water systems or flood control); Consulting Services (e.g., feasibility studies, advisory and management consulting, training and capacity building); or General Support Services (e.g., security, janitorial, transportation and logistics, training and event management). It also describes the objective of the project. |  | Refers to quantity / size of the contract (whether by lot, item or package). If items are too many to use this column, a separate attachment may be included) Item refers to the smallest unit or individual good/service being procured. Lot refers to a group or related items bundled together in one bidding. Package is a collection of one or more lots grouped under a single procurement project It is sufficient to indicate that this information is reflected in the Technical Specifications, Scope of Work (SOW), or Terms of Reference (TOR) (as applicable) when the latter is attached to this PPMP. | Indicate applicable procurement mode under RA No. 12009 recommended by the End-User. | Indicate the projected month (MM/YYYY) of the Pre-procurement Conference | Indicate the projected month (MM/YYYY) of the start of procurement activity which will depend on the applicable mode of procurement used by the Procuring Entity. (e.g. Publication for Competitive Bidding; Posting of RFQ (if required) for SVP, as the case may be). | Indicate the projected month (MM/YYYY) of issuance of Notice of Award or Purchase Order, as the case may be, based on the prescribed procurement timelines. | This refers to the target start date (MM/YYYY) when the delivery of goods, implementation of infrastructure projects, or provision of consulting services is expected to begin, indicating when the project is needed. The End-User may indicate "as needed" if the project is on a "per need" basis, i.e repair works | The fund source for the payment of the project to be procured may include, but shall not be limited to the following: General Appropriations Act (GAA) for NGAs, Corporate Operating Budget for GOCCs and GFIs, Internally Generated Funds for SUCs, General or other sources of fund for LGUs, Special Purpose Funds or Trust Funds for special allocations/donor or grants, and Foreign Assisted Projects (FAPs) for projects funded by development partners. | Use Estimated Budget when the GAA or other appropriate fund source has not yet been passed or approved and Authorized Budgetary Allocation when the GAA or other appropriate fund source has been passed or approved. It is understood that these amounts have been determined after the conduct of market scoping. |  | This column refers to the additional details regarding the project, such as, but not limited to the following: a. basis of changes from previous PPMP b. contract package details : i.e, estimated budget for the whole period (in case of multi-year contracts) c. Procurement Strategies to be used. d. Recommended Award criterion (Lowest Calculated and Responsive Bid (LCRB), Most Economically Advantageous Responsive Bid (MEARB), Most Advantageous Responsive Bid / Highest Rated Responsive Bid (MARB/HRRB), Lowest Comparative or Competitive Responsive Bid (LCCRB)
TOTAL BUDGET:
| Prepared by: |  |  | Submitted by:
| Signature over Printed Name |  |  | Signature over Printed Name
| Position/Designation |  |  | Position/Designation
| [End-User or Implementing Unit] |  |  | [Head of the End-User or Implementing Unit]
| Date : _________________ |  |  | Date : ____________

## Guide to Fill-Out
Guide to Filling Out the PPMP Form
Particular |  | Basis/References, if any | Notes | Illustration/Examples
|  |  |  | Goods | Infrastructure | Consulting
Heading | Title of the Document "Project Procurement Plan No. ___" | IRR of RA No. 12009- Section 7.7.2 to 7.7.3 | Indicate the Project Procurement Management Plan No. (first submitted version of the Indicative PPMP as No. 1, succeeding update/final PPMP as No. 2, and so on), then place a check (✔) whether the PPMP is Indicative or Final, in consideration of the following: An "Indicative" PPMP is being prepared as part of the budget proposal preparation, while the budget allocation is not yet approved/final. A Final PPMP is being prepared as a result of the final and approved budgetary allocation of the General Appropriations Act, corporate operating budget or appropriation ordinance, as the case maybe. | - | - | -
Column No. 1 | General Description and Objective of the Project to be Procured | IRR of RA No. 12009- Section 7.7.1 (b) | Provide a concise but clear description of the project and its intended purpose. Indicate whether the project will be implemented through procurement or by administration. If applicable, specify whether the activity supports a program, mandate, or operational need. | Supply and Delivery of Uniform long sleeve T-shirt with Print, Shovel and Wheelbarrow for Billy Bayong Program of National Road and Bridges, X Office, Brgy. X, Municipality of X, X City | Improvement and repair of existing facilities, buildings, and structures and Proposed construction of the Billy Bayong Sports Complex in the XX Region, including a covered walkway (by Administration) | Procurement of Technical Assistance for QMS Implementation towards ISO 9001:2015 Certification
Column No. 2 | Type of the Project to be Procured (whether Goods, Infrastructure and Consulting Services) | IRR of RA No. 12009- Section 7.7.1 (b) | Indicate the type of procurement—whether for Goods, Infrastructure Projects or Consulting Services. If classified as General Support Services, indicate Goods (General Support Services). | Goods | Infrastructure | Consulting Services
Column No. 3 | Quantity and Size of the Project to be Procured | IRR of RA No. 12009- Section 7.7.1 (c) | Indicate the quantity and size of the procurement activity. If the projects consists of lots, each lot must be presented in a separate row, especially when multiple lots are involved. If the number of items is too large to fit in this column, a separate attachment may be used. Guide on Quantity and Size as defined by Procurement Category 1. Goods • Quantity : The total number of individual items or units to be supplied. Example: Ordering 200 desktop computers means the quantity is 200. • Size : The physical dimensions, capacity, or specification of each item. Example: Each computer must have a 15-inch monitor and 16GB RAM. 2. Infrastructure Projects • Quantity : The total extent or number of components to be constructed or installed. Example: Building 3 bridges or laying 500 meters of road. • Size: The scale, dimensions, or capacity of each component or structure. Example: Each bridge must be 50 meters long, or the road must be 6 meters wide. 3. Consulting Services • Quantity : The number of consultants, teams, or person-months required for the assignment. Example: Engaging 2 consulting teams or contracting for 12 person-months of expert input. • Size: The scope, scale, or coverage of the consulting assignment, such as the organizational level or geographic area impacted. Example: Consulting on a nationwide IT system rollout, or an assignment covering five provinces. These definitions ensure clarity in procurement documents, helping suppliers and service providers understand both how much is needed (quantity) and the specific requirements or scale of each unit or assignment (size). | [For the Billy Bayong Program for National Road and Bridges, X Office, Brgy. X, Municipality of X, X City] Lot 1 Quantity : 14,000 pcs. short-sleeved T-shirts with print 14,000 pcs. handtowels Size : T-shirt: standard adult size with front and/or back print Handtowel: 8 inches x 12 inches, cotton fabric Lot 2 Quantity: 2,200 pcs. shovels 1,300 pcs. wheelbarrows Size : Shovel: standard length, e.g., 38 inches long with a steel blade and wooden handle Wheelbarrow: single-wheel, heavy-duty steel tray with 65 liter capacity | [For the Improvement/ Repair of Existing Structures and Construction of Sports Complex] Quantity: Two (2) components: 1.Improvement and repair of existing building and structures 2. Construction of sports complex with covered walkway Size: 1. Floor area to be rehabilitated- 500 sq.m. 2. Sports Complex- 30 m x 50m structure with seating capacity for 500 persons and a covered walkway 60m long x 3 m wide, steel frame with concrete pavement and roofing. | [For the Procurement of Technical Assistance for QMS Implementation Towards ISO 9001:2015 Certification] Quantity: One (1) consultancy engagement Size: Full implementation of a QMS compliant with ISO 9001:2015 to cover all functional units of the XXX agency
Column No. 4 | Recommended Mode of Procurement | IRR of RA No. 12009- Section 7.7.1 (d) | Indicate applicable procurement mode under RA No. 12009. The Bids and Awards Committee shall recommend to the Head of the Procuring Entity the use of any of the modes of procurement through the Annual Procurement Plan. | Competitive Bidding | N/A (To be undertaken by Administration) | Negotiated Procurement - Highly Technical Consultant
Column No. 5 | Pre-Procurement Conference, if applicable | IRR of RA No. 12009- Section 7.7.1 (e) | Indicate yes or no if the Pre-proocurement Conference is to be undertaken in accordance with the RA No 12009 and its IRR. | Yes | N/A | No
Column No. 6 | Start of Procurement Activity | IRR of RA No. 12009- Section 7.7.1 (e) | Indicate the projected month and year (MM/YYYY) of the start of procurement activity which will depend on the prescribed procurement timeline of the applicable mode of procurement used by the Procuring Entity (e.g. Pre-procurement Conference, Publication, Posting, Issuance of the RFQ, as the case may be). | 04/2026 | N/A | 03/2026
Column No. 7 | End of Procurement Activity | IRR of RA No. 12009- Section 7.7.1 (e) | Indicate the projected month and year (MM/YYYY) of issuance of Notice of Award or Purchase Order, as the case may be, based on the prescribed procurement timelines of the applicable mode of procurement used by the Procuring Entity. | 05/2025 | N/A | 03/2026
Column No. 8 | Expected Delivery/ Implementation Period |  | Indicate the month and year (MM/YYYY) of the expected delivery of goods or implementation of the project, as the case may be. | 07/2025 | 06/2026 to 06/2028 | 03/2026 to 08/2026
Column No. 9 | Source of Funds |  | Indicate the proposed source of fund for the Project. This may include, but is not limited to: the General Appropriations Act - Current or Continuing, Corporate Operating Budget, Appropriation Ordinance, Internally Generated Income, Special Purpose Fund, Trust Fund, or Foreign-Assisted Fund, consistent with the agency’s approved budget documents. | GAA 2026 - Current Appropriation | GAA 2024 - Continuing Appropriation | Internally- Generated Income
Column No. 10 | Estimated Budget / Authorized Budgetary Allocation | IRR of RA No. 12009- Section 7.7.1 (f) | Indicate Estimated Budget on Indicative PPMP when the GAA or other appropriate fund source has not yet been passed or approved. Otherwise, indicate the Authorized Budgetary Allocation on Final PPMP when the GAA or other appropriate fund source has been passed or approved. | Php12,499,544.00 | Php15,900,000.00 | Php750,000.00
Column No. 11 | Attached Supporting Document/s | IRR of RA No. 12009- Section 7.7.1 (g) and Section 10 | Indicate the supporting documents for each corresponding Project attached to the PPMP, which includes the Market Scoping Checklist and other relevant documents such as Technical Specifications, Detailed Engineering, Scope of Work or Terms of Reference and any equivalent document as applicable. NOTE: The duly accomplished Market Scoping Checklist for each procurement project is a mandatory supporting document to the PPMP. | Technical Specifications | Scope of Work, Engineering. Plan, Feasibility Study | Terms of Reference
Column No. 12 | Remarks |  | Indicate additional details regarding the Project, such as, but not limited to the following: a. Basis of changes from previous PPMP b. Contract package details : i.e, estimated budget for the whole period (in case of multi-year contracts) c. Procurement Strategies to be used | Updated ABC due to bid failure under BAC Resolution No. xx-2026, proposing for Framework Agreement | To be undertaken by Administration c/o the Engineering Department | -

## Reference 4 - MYCA Form
Disclaimer: The Multi-Year Contracting Authority (formerly Multi-Year Obligational Authority) is a document issued by DBM either for locally funded projects or foreign assisted projects implemented by agencies in order to authorize the latter to enter into multi-year contracts for the full project cost. For guidelines on securing MYCA from the DBM, please refer to DBM Circular Letter No. 2015-7 dated 3 June 2015. In the case of GOCCs and LGUs whose fund sources are not covered by the GAA, an equivalent document shall be issued to pursue any Multi-Year Project. Any question or clarification regarding the form shall be directed to the appropriate agency.